## Sheet1
Actors | Requirements | To Do | Story Points | Risk Level
Glossary | Scannable QR code | have scannable QR code | 1 | low
Players | US 01.01.01 Add new QR code to account | Add QR codes from main page | 1 | low
| US 01.02.01 View previously added QR codes | Inventory of Qr codes | 1 | low
| US 01.03.01 Delete QR codes from account | Delete function | 1 | low
| US 01.04.01 Sort QR codes by points | Sort function - based on point value | 2 | low
| US 01.05.01 Sum up QR code points | Sum function - based on point value | 1 | low
| US 01.06.01 Total amount of QR codes | Count total list | 1 | low
| US 01.07.01 See other peoples account | Online connection? Database? | 8 | high?
| US 05.01.01 Search other players | Search database | 3 | low
| US 07.01.01 See highscores and own rank | Sort database off points? | 2 | low
| US 04.01.01 Have unique username | Individual player profiles as objects, sort database off username? | 1 | low
| US 04.02.01 Save profile to phone to avoid log in | Save local data to phone | 8 | high
Game QR Code | Scan QR code | QR Scanner | 2 | medium
| US 02.02.01 Comment on QR code | Inventory of all QR codes, unique comments are stored | 3 | medium
| US 02.03.01 Browse codes other players have found | Database of all Qr codes? | 2 | low
| US 02.04.01 See other players with the same QR code | QR code database stores users, search database for users | 2 | medium?
| US 02.05.01 QR codes have a unique name | Create name based off hash, check uniqueness | 1 | low
| US 02.06.01 QR codes have a unique image | Create image based off hash, check uniqueness | 1 | low
| US 08.01.01 Hide actual QR code | Store QR as hash, cannot be reversed | 1 | low
| US 09.01.01 Avoid showing large images | Check size before uploaded to database | 1 | low
Location | US 06.01.01 See a map of QR codes | Have map view | 8 | high
| US 02.01.01 Record a photo of object or location or not if chosen | Prompt user to take picture or skip, save to QR database | 5 | high
| US 08.02.01 Record location of object, or not if chosen | Record location to database | 2 | low
| US 05.02.01 Search QR codes by location | Search database by QR code location, ignore null | 2 | low