## Sheet1
Actors | Requirements | To Do | Story Points | Risk Level
Glossary | Scannable QR code | have scannable QR code | 1 | low
Players | Add new QR code to account | Add QR codes from main page | 1 | low
| View previously added QR codes | Inventory of Qr codes | 1 | low
| Delete QR codes from account | Delete function | 1 | low
| Sort QR codes by points | Sort function - based on point value | 2 | low
| Sum up QR code points | Sum function - based on point value | 1 | low
| Total amount of QR codes | Count total list | 1 | low
| See other peoples account | Online connection? Database? | 8 | high?
| Search other players | Search database | 3 | low
| See highscores and own rank | Sort database off points? | 2 | low
| Have unique username | Individual player profiles as objects, sort database off username? | 1 | low
| Save profile to phone to avoid log in | Save local data to phone | 8 | high
Game QR Code | Scan QR code | QR Scanner | 2 | medium
| Comment on QR code | Inventory of all QR codes, unique comments are stored | 3 | medium
| Browse codes other players have found | Database of all Qr codes? | 2 | low
| See other players with the same QR code | QR code database stores users, search database for users | 2 | medium?
| QR codes have a unique name | Create name based off hash, check uniqueness | 1 | low
| QR codes have a unique image | Create image based off hash, check uniqueness | 1 | low
| Hide actual QR code | Store QR as hash, cannot be reversed | 1 | low
| Avoid showing large images | Check size before uploaded to database | 1 | low
Location | See a map of QR codes | Have map view | 8 | high
| Record a photo of object or location or not if chosen | Prompt user to take picture or skip, save to QR database | 5 | high
| Record location of object, or not if chosen | Record location to database | 2 | low
| Search QR codes by location | Search database by QR code location, ignore null | 2 | low